## Sheet1
Sprint Plan Summary
Sprint | Weeks / Dates | Focus | Key Deliverables | Owners / Inputs | Gate / Exit Criteria | Dependencies / Notes
Sprint 1 | Weeks 1–2 · August 17–28 | Infrastructure & Environments | Greenfield repo initialized from Angular starter; dev/staging AWS environments; Aurora PostgreSQL; Redis; ECS Fargate placeholders; Secrets Manager paths; GitHub Actions and CODEOWNERS; Keycloak staging setup; synthetic data seed script; offshore dev access; LaunchDarkly project. | DevOps for AWS provisioning; Onshore Tech Lead for Keycloak, secrets paths, and offshore access; Offshore Backend Lead for synthetic data script and repo scaffold. | Repo isolated, dev AWS account has no connectivity to existing LINQ accounts, offshore individual accounts provisioned, and design package delivered. Onshore Tech Lead and DevOps sign off before offshore kickoff. | Offshore team starts only after access, isolation, and design package are confirmed.
Sprint 2 | Weeks 3–4 · August 31–September 1 | Database Schema & Platform Services | cnp_global migrations; cnp_ops demo-state schema; IsFederal triggers; DB roles; initial ConfigDefinitions and PovertyGuidelineHistory seed; .NET 8 API scaffold; MediatR, FluentValidation, exception middleware; config and permission services; JWT validation; tenant context; healthcheck; Keycloak realm and users. | Backend team with Onshore Tech Lead validation. Platform service decisions must align with database and workflow design docs. | IsFederal triggers reject federal-locked override writes; tenant context middleware sets schema per JWT claim; offshore team cannot connect to staging from dev environment. | DTO boundary and MediatR folder structure must be enforced before Sprint 3.
Sprint 3 | Weeks 5–6 · September 14–25 | Workflow Engine & Named Hooks | WorkflowEngine service; named hook registry; FreezeClaimLaws, AllClaimErrorsResolved, NoNDLMatch, and demo-state hook; workflow seed data; tenant transition override; hook unit tests; IsFederal guardrail assertion tests. | Onshore Tech Lead reviews all named hooks, federal seed data, and guardrail test results. Onshore config specialist identifies demo-state hook before sprint start if possible. | Guardrail tests prove FreezeClaimLaws cannot be removed, direct DB delete of federal condition raises exception, and exception is logged to AuditLogs. | If demo-state hook is not ready, Sprint 3 may proceed and add it in Sprint 4.
Sprint 4 | Weeks 7–8 · September 28–October 9 | Application Domain | Application domain tables; AuditLogs, EntitySnapshots, FieldChangeLog; ClaimLaws table; application commands and queries; audit and snapshot writes; ClaimLaws creation through FreezeClaimLaws; 30–50 synthetic applications; lifecycle integration tests; API contracts finalized. | Backend team with API contract review before frontend build begins. | Submit → UnderReview → Approved lifecycle passes; ClaimLaws row exists after approval; AuditLogs and EntitySnapshots exist for every transition; API contracts are published and frozen. | Frontend Sprint 5 depends on stable API contracts from this sprint.
Sprint 5 | Weeks 9–10 · October 12–23 | Frontend — Shell, Auth, Application List | Angular 17+ app with snackpaq design system; OIDC login; route guards; role-based navigation; application list with paging, status filter, sponsor search; role-aware data access; loading, error, and empty states; responsive layout. | Frontend team. Onshore config specialist provides demo-state program names, list labels, and status labels. | End-to-end login → application list flow works in staging for Caseworker, Reviewer, and LINQConfigAdmin; direct Caseworker access to Reviewer endpoint returns 403. | Token is stored in service memory only; no localStorage or sessionStorage.
Sprint 6 | Weeks 11–12 · October 26–November 6 | Frontend — Workflow, Audit Trail, Speed Demo Screen | Application detail page; workflow action buttons; approval ClaimLaws summary; audit trail panel; demo-state-specific field; Redis integration in ICnpConfigService; cache-bust endpoint; Config Admin screen for one key editor. | Frontend and backend teams. Onshore config specialist identifies speed-demo config key and legacy-equivalent story. | Dry run confirms config change is made in Config Admin, visible in workflow within 5 minutes, cache bust is logged, and full sequence is timed. If over 8 minutes, investigate before Sprint 7. | Speed-demo key must be Tier 1 or Tier 2, visible in workflow, and not IsFederal=true.
Sprint 7 | Weeks 13–14 · November 9–20 | Demo State UAT & Data Validation | UAT environment from Sprint 6 tag; curated 50–100 application synthetic dataset; demo-state informal UAT; issue log; high-priority fixes; 10–20 workflow validations; internal dry-run demo; IsFederal guardrail regression suite. | Onshore Tech Lead, account team, engineering, and demo-state participants. LINQ account team facilitates UAT. | Demo-state contact confirms UAT is satisfactory; internal dry run completes in 30 minutes or less with no failures; high-priority issues closed; guardrail suite passes; Onshore Tech Lead approves demo release tag. | No claims workflow, FNS report work, or new feature expansion in this sprint.
Sprint 8 | Weeks 15–16 · November 23–December 4 | Demo Environment Freeze & Final Prep | Demo environment deployed from approved Sprint 7 tag; code freeze; smoke test by someone unfamiliar with the demo; performance validation; final demo data check; fallback plan; account team briefing; invite list confirmed. | Onshore Tech Lead declares demo-ready. Account team prepares script, Q&A, and logistics. Offshore team works only on post-prototype backlog. | Smoke test passes; performance targets met; demo environment stable; Onshore Tech Lead formally declares demo-ready; first state demo scheduled. | No offshore changes to demo environment. Freeze is absolute; staging on identical tag is the fallback.

## Sheet2
feature name/JIRA ticket